Prototype Carbon Fund

Romania: Afforestation of Degraded Agricultural Land Project

###### Project Design Document

This Project Design Document (PDD) is provided in anticipation and for the purpose of the registration of the Afforestation of Degraded Agricultural Land Project in Romania as Joint Implementation (JI) project under Art. 6 Kyoto Protocol (KP). The PDD and its supporting documents (Baseline Study, Monitoring Plan, etc.) describe the project design in regard of the objectives and requirements of and modalities for JI. The PDD is thus a key document for the validation of the project.

List of Contents

1	Key Project Parameters	2

2	Project Entities	4

3	Project and Sector Background	4

4	Project Description	5

5	Global Environmental Benefits	6

5.1	Project Baseline and Environmental Additionality	6

5.2	Monitoring and Verification	8

5.3	Emission Reduction Projections	10

6	Local Environmental and Socio-Economic Benefits	10

7	PCF Due-Diligence and Expected JI Process Requirements	12

8	Project Documents	12

9	Emission Reductions Detail	14

# Key Project Parameters

The following Table presents a summary of key project data. More information is provided in the following sections and tables and in the documents referenced in Section 8.

Table 1	Project Summary

| Project objectives | Afforestation of 6,728 ha of State-owned degraded agricultural lowlands in the southwest and southeast of the Romanian Plain and the ecological reconstruction of part of the Lower Danube floodplain through the planting of native species. |
| --- | --- |
| Project location | 7 counties of southwest and southeast Romania: Dolj, Mehedinti, Olt, Braila, Galati, Tulcea and Vaslui. |
| Type of project | CO2 sequestration: Afforestation. Species selection is based on local site conditions and management objectives (fertility, soil stabilization, ecological reconstruction). The main species for degraded lands is Robinia (Robinia pseudoaccacia), a naturalized species which has been planted extensively in Romania over the past century. Where site conditions permit, oak and other broadleaf tree (Quercus cerris) and shrub species will be planted. On the Lower Danube Floodplain native Poplars (Populus alba and Populus nigra) will be planted with some native Willow (Salix spp). |
| Project baseline | Business as usual scenario: Continued low-quality grazing (pasture). Very little afforestation would take place, in line with statistical evidence for the past decade and due to the very low internal rate of return on such investments. |
| Crediting period | Fifteen years: The project seeks Emission Reduction Units (ERUs) under Art. 6 KP for a 15-year period. |
| Estimated CO2 reduction | Emission reductions (ERs): 2002 – 2007: 212,697 2008 – 2012: 410,046 2013 – 2017: 395,416 15 year crediting period: 2002 – 2017: 1,018,161 |
| Sources of ERs | Only CO2. ERs will be achieved through sequestering carbon in above and below ground biomass and in soils. |
| Sustainable development impact | The project contributes to sustainable development in Romania through - stabilization of impoverished soils through protection against wind and water erosion - reconstruction of ecosystem affected by agriculture (Small Island of Braila) - generation of employment for afforestation works |
| Project financing | Estimate of total project cost in US$: $10.1 million All the financing will be provided by the National Forest Administration. |
| Project revenues (including sale of CO2 reductions) | - The project will generate revenues from the sale of timber from thinnings (all species) and harvesting (all species except poplar). Thinnings start in year 6 and are recurrent according to a timetable specific to each species. Robinia is harvested after 30 years. - Sale of CO2 ERs to the PCF and other buyers at US$ 3.6/t CO2e is estimated at US$ 3.67 million in nominal terms in the 15 year crediting period - Estimated PCF purchase value: US$ 3.67 million. |
| Host country approval | The project was endorsed by the Ministry of Water and Environmental Protection, which chairs the National Commission on Climate Change and is the focal point in Romania for climate change related matters (including the GEF). Romania is an Annex I Party to the UNFCCC. Romania ratified the Kyoto Protocol on March 19, 2001. |
| Project start | Fall 2002. Afforestation, i.e. establishment of the plantations, will be complete within 4 years of project start. |

# Project Entities

The project is sponsored by the National Forest Administration, the public forest administrator in Romania, in charge of around 90% of Romanian forests. The NFA was established in 1996 as a legal state-owned entity with an essentially commercial mandate. The public company had first been created by Government Decision No. 1335/ December 1990 under the name Autonomous Forest Administration. The NFA operates as a financially autonomous organization performing forest management and silvicultural operations, engaging in non-timber forest products and services and providing a range of public service functions. It reports to the State Secretary for Forests within the Ministry of Agriculture, Food and Forests (Direction of Forests, DF). The NFA has a broad scope of activities it is required to undertake, in addition to the normal range of management and silvicultural activities, including the following: manage private or community-owned forests on an agreement basis; lease or rent assets; and purchase or accept donations of privately owned lands for afforestation. The NFA is responsible for the administration and management of protected forest areas including national parks. It is also obliged to ensure that state forests contribute to improvement of the environment and ensure supply of wood for the national economy.

Table 2	Project Partners and Support

| Project sponsor | National Forest Administration Bucharest, Bd. Magheru nr.31, Romania Contact Person: Mr. Ciprian Pahontu Phone/Fax: 40-1-212-9741 x255 / 40-1-212-9769 E-mail: s.regpad@rosilva.ro |
| --- | --- |
| Project Operator | National Forest Administration Bd. Magheru nr.31, 70164 Bucharest, Romania Contact Person: Mr. Ciprian Pahontu Phone/Fax: 40-1-212-9741 x255 / 40-1-212-9769 E-mail: s.regpad@rosilva.ro |
| Project planning and assistance | - World Bank, Europe and Central Asia Region, Environmentally and Socially Sustainable Development (1818 H St NW Washington DC 20433): Benoît Bosquet, Task Manager, bbosquet@worldbank.org, Tel: 1-202-458-0923 - World Bank Prototype Carbon Fund (1818 H St NW Wash. DC 20433): Benoît Bosquet, Natural Resources Management Specialist, bbosquet@worldbank.org, Tel: 1-202-458-0923 |

# Project and Sector Background

The National Forest Policy and Strategy (NFPS) was developed in 2000 with World Bank support. It was the first open, transparent and consultative forest policy and strategy development process and involved representatives of the main forest stakeholders in the country. It was endorsed by the Ministry of Water, Forests and Environmental Protection, the Ministry of Industries and the Ministry of Education in December 2000. Afforestation of degraded agricultural lands is one of the strategic actions foreseen.

The Romanian public authority responsible for forests is the Department of Forests (DF) in the Ministry of Agriculture, Food and Forests (MAFF). The DF has two Directorates including the Forest Inspectorate and the Strategy, Policy & Legislation Directorate, both of which report directly to the Secretary of State for Forests. The regulatory functions are contained within the Strategy, Policy & Legislation Directorate, while the support function is concentrated in the newly formed Private Forests Management Office.

The National Forest Administration (NFA) is responsible for managing State forestland (December 2001 circa 90% of all forests), under policy and legislative direction from the Department of Forests. Government Decision No. 173 (January 2001) determines the scope and type of activities that can be undertaken by the NFA. These are broad and enable the NFA to undertake, in addition to the normal range of management and silvicultural activities, the following: forest management on private or communal forests on an agreement basis; lease or rent of assets; and purchase of private owned lands for afforestation. The NFA is responsible for the administration and management of protected forest areas including national parks. It is also in charge of ensuring that state forests contribute to environmental quality and supply wood for the national economy.

The Romanian forest sector is undergoing far-reaching reforms, one of the most important of which is the restitution of forestland to pre-1948 owners. Under this policy, 40% of the forests managed by the NFA could be restituted to individuals and communities.

# Project Description

The project concerns the afforestation (manual and mechanized) of degraded agricultural lands in the southwest and southeast of the Romanian Plain and the ecological reconstruction of part of the Lower Danube floodplain (Braila and Olt Counties) through the planting of native species. Species selection is based on local site conditions and management objectives (fertility, soil stabilization, ecological reconstruction). The main species for degraded lands is Robinia (Robinia pseudoaccacia), a naturalized species which has been planted extensively in Romania over the past century. Where site conditions permit, oak and other broadleaf tree and shrub species will be planted. On the Lower Danube Floodplain native Poplars (Populus alba and Populus nigra) will be planted with some native Willow (Salix spp).

The total afforestation area included in the project is 6,728 hectares (net of roads and buildings etc.) and is spread across seven counties.

Apart from 500 hectares on the small Island of Braila, which belong to NFA and are currently being planted, all lands are under the stewardship of the State Domain Agency (SDA) and are in the process of being transferred to the NFA. The transfer will take place on the basis of a Government decision made in April 2002 (Decision no. 357 of April 15, 2002).

The project conforms with overall State forest policy and strategy which identifies degraded agricultural lands for afforestation. There is an estimated 3 million hectares of degraded agricultural lands in Romania.

The project’s degraded lands have been worked intensively for agriculture since the early seventies, coinciding with the extension of the drainage of the river Danube. Initially these lands produced a range of crops including cereals, vegetables, fruits and grapes. Through excessive working and lack of investment in irrigation infrastructure and maintenance, the lands have become degraded and subject to erosion and are now uneconomic for crop production and are either used mainly for pasture or abandoned.

The project period is 30 years, which corresponds to one Robinia rotation. This is different from the purchasing period, which was set at 15 years. In this manner the total purchase volume by the PCF (1 MtCO2e) is about half the 100 year average carbon sequestration (1.9 MtCO2e). Please see the details in Section 9.

# Global Environmental Benefits

## Project Baseline and Environmental Additionality

In this project, the baseline scenario is defined as the most likely land use scenario for the land selected for afforestation.

The argument that this project is additional is built on two pillars: (1) simple consideration of historical evidence; and (2) comparison of the financial merits of alternative land-use options.

First, Romania has a policy of afforesting 25,000 ha of degraded agricultural land per year. Yet, the NFA has afforested an annual average of 345 hectares over the past ten years. The main reason why so little land has been afforested is that NFA has not found the economics of such an investment attractive. This suggests that, in the absence of carbon finance, the business as usual scenario would prevail, in other words little or no afforestation would take place. However, this argument is backward-looking. It needs to be backed up with a forward-looking approach.

Second, the forward-looking methodology proposed to determine the baseline scenario and establish additionality of the project is financial analysis. The method consists of selecting a number of feasible land-use options for the land included in the project and determining which one is the most likely to materialize in light of financial considerations (costs and benefits). The net present value (NPV) and financial internal rate of return (FIRR) are calculated for each of these options. The option with the highest NPV or FIRR is considered as the baseline scenario.

The options include: pasture, grain and fruit crops, total abandonment and afforestation. Grain and fruit crops, selected in agreement with the Central Research Station for Agricultural Crops on Sands, are: maize; winter wheat; water melon; vines; and orchard (peach).

The project area can be divided into two quite separate components: (i) degraded agricultural lands; and (ii) the Lower Danube Floodplain. The degraded lands have very poor site productivity and in the absence of carbon credits are incapable of yielding anything like an economic return. The overall FIRR in the absence of carbon credits is 2.04%. This is less than the FIRR of pasture, which can be considered as the baseline scenario. With carbon credits, the IRR increases to 3.86% for the overall project (components (i) and (ii)), which is slightly better than pasture. Other land use options produce much worse results.

Hurdle discount rates have been developed for use in forestry investment decision making and represent the minimum FIRR required to undertake the investment. The rates vary depending on ownership category (state, private), perceived risk and alternative opportunities for investment but are within the range of 2.5 to 7% for State forestry.

The project FIRR without carbon is lower than minimum hurdle rates and thus would not normally be considered for investment. The with-carbon IRR shows a return which some other State forestry organizations might consider worthwhile. Thus it is reasonable to conclude that the project areas would not be afforested in the absence of carbon credits.

The afforestation of the Lower Danube Floodplain represents a special case – it is ecological restoration.  No harvesting will take place and consequently no timber revenues will ensue. Thus this area could not be considered as part of the normal afforestation undertaken by the NFA since 1991. It is only possible to afforest these areas under the project and with the inclusion of carbon credits.

Thus considering the economics of the project, the area would not normally be planted under commercial criteria.

The NFA has afforested an annual average of 345 hectares over the past ten years. Can afforestation of that area be considered additional? Yes, for the same reason that such afforestation is not profitable and would not be undertaken if the NFA did not pursue environmental objectives, which create positive externalities for society at large. Simple pasture has a higher FIRR, but afforestation generates additional benefits, which are difficult to value and do not accrue to the NFA, such as soil and microclimatic improvements, erosion control, enrichment of biological diversity, etc.

In sum, the total project area can be considered as eligible under the additionality criterion both from an economic and technical viewpoint.

Table 3	Baseline and Additionality Issues

| “Issue” Area | Explanation |
| --- | --- |
| Project baseline | Business as usual (BAU) scenario: Continued low-quality grazing (pasture), which has the highest FIRR and NPV of all the land-use options before carbon finance. |
| Baseline methodology | Financial analysis: The method consists of selecting a number of feasible land-use options for the land included in the project and determining which one is the most likely to materialize in light of financial considerations (costs and benefits). The NPV and FIRR are calculated for each of these options. The option with the highest NPV or FIRR is considered as the baseline scenario. |
| Plausible scenarios | The NFA has afforested an annual average of 345 hectares over the past ten years. The main reason why so little land has been afforested is that NFA has not found the economics of such an investment attractive. This suggests that, in the absence of carbon finance, little or no afforestation would take place. |
| Baseline drivers | Cost of afforestation and availability of land for afforestation. |
| Geographical boundary | The 6,728 ha afforested under the project. |
| System boundary | The 6,728 ha afforested under the project. No leakage is expected. |
| Time boundary | 15 years |
| Leakage | No leakage identified. |
| GHG coverage | Only CO2 is relevant and can be claimed. |
| Environmental additionality | Real ERs are calculated based on ex post verification that the trees are alive grow. |
| ODA and environmental additionality | No ODA in the project. The project will be financed by the NFA’s own resources. |
| Funding (ODA) additionality | No ODA in the project. |

## Monitoring and Verification

Instructions for monitoring, ER calculation and verification are contained in the Monitoring Plans (MPs) for the Afforestation of Degraded Agricultural Land Project, which are part of the design documents. The following Tables presents an overview of the MPs. Please refer to the MPs for details.

Table 4	Monitoring and Verification Provisions

| “Issue” Area | Explanation |
| --- | --- |
| Monitoring | The NFA will establish a number of permanent measurement and monitoring plots (sample plots), the exact number of which depends on the level of precision desired. The quantity of carbon accruing on the planted sites will be measured over the length of the project and over separate time periods. This is accomplished by measuring the changes in stocks over time. In the first few years, if will suffice to count the number of trees and take photographs. Actual measurements don’t start until canopy closure. For forest vegetation, this will be accomplished by monitoring the growth of individual trees in permanent sample plots at given time intervals (5 years), keeping track of growth of survivors, mortality and ingrowth of trees. The NFA annually monitors newly afforested areas until canopy closure (required by law), which in these afforested lands with lower site classes is going to occur over at least the first five years. This NFA monitoring will be able to ensure that the project is on track during this critical time. Changes in carbon per tree will be estimated and summed per plot. Changes in carbon stocks in dead wood, and fine litter will also be measured and added to those for the trees. Statistical analyses will then be performed on net carbon accumulation per plot; rates of carbon accumulation will be estimated directly from these analyses. In contrast to the procedure for vegetation where the original trees in the plots are monitored through time, the same soil sample cannot be monitored over time. Instead, at each sampling interval (every 10 years) a new sample is collected and the analyses will involve subtracting two large pools from each other. Each year, estimation of changes in carbon stocks will done using the software CO2Fix and every 5 years for forest plots and every 10 years for soil plots, an adjustment will be made to the estimation based on field measurements. |
| Calculation of ERs | CO2Fix model will be run on an annual basis, with corrections being made every 5 years following field measurements. |
| Date needs | Annual monitoring by the NFA including counting surviving trees and taking photographs for the first 4-5 years; annual estimation using CO2Fix; field measurements every 5 years on forest plots and every 10 years on soil plots. |
| Conservative ER estimates | The ER estimates from CO2Fix and on which the PCF purchase will be based have used conservative parameters, growth rates, data selection and methodology. This is illustrated by the fact that field measurements conducted during the baseline study returned higher carbon sequestration figures than the CO2Fix estimates. |
| Verification | ERs are verifiable: ERs based on CO2Fix simulations and field measurements following a standard protocol. A monitoring management and operational system will be established including clear responsibilities, transparent record keeping, training, quality control, auditing procedures and verification. |
| Baseline, MP revision | Not applicable. |
| Sustainable Development | The MP defines indicators of socio-economic and environmental impact of the project. Socio-economic indicators including employment and the incidence of illegal grazing. Environmental indicators include species diversity and abundance. Both of these sets of indicators will be followed every 5 years. |

## Emission Reduction Projections

- Emission reductions will follow the S-shaped biomass growth curve for the various species and productivity classes established in this project. Emission reductions will be equal to the difference between the carbon sequestered in above and below ground biomass and in soils in the project and the carbon emissions due to the project, namely the death or destruction of Amorpha and other vegetation types, plus the diesel burnt by the tractors and other machinery in the process of afforestation (site and soil preparation, hole digging, etc.).

- Carbon sequestration will be claimed for a 15-year period beginning in the fall of 2002. The emission reductions (ERs) are in the table below. Details can be found in Section 9.

| - Period | - Estimated emission reduction (tCO2e) |
| --- | --- |
| - 2002-2007 | - 212,697 |
| - 2008-2012 | - 410,046 |
| - 2013-2017 | - 395,416 |
| - Total (for 15 year crediting period) | - 1,018,160 |

# Local Environmental and Socio-Economic Benefits

This project will obviously expand the national forest cover, which is a national objective. Furthermore, the project will enhance biological diversity by turning impoverished agricultural land into forests, one direct and monitorable benefit of which should be the increasing diversity in bird species nesting in the area. Other benefits, which will not be systematically monitored in the course of project implementation, will include soil stabilization, and microclimatic improvements.

The project will create employment through afforestation works and is expected to contribute to improving agricultural yields in the areas surrounding the newly afforested sites.

Table 7	Domestic and Local Project Benefits

| “Issue” Area | Explanation |
| --- | --- |
| Local environmental benefits | - Expansion in forest cover. - Enhanced biological diversity, in particular bird species. - Protection against wind and water erosion of soils. - Microclimatic improvements. |
| Socio-economic benefits | - Employment creation to fulfill afforestation - Improvement in agricultural yields thanks to microclimatic improvements and better moisture retention. |
| Capacity building | - Extensive pre-negotiations consultations have been carried out. - A Grant has been requested from a Japanese Trust Fund administered by the World Bank to finance a communication program that would benefit both local communities and the NFA. |
| Technology transfer | - Demonstration that carbon finance can promote the national goal of afforestation. |
| Host Country criteria | - The Ministry of Water and Environmental Protection has endorsed the project and is expected to formally approve it through the Host Country Agreement. - The project is consistent with the World Bank’s Country Assistance strategy. |
| Sustainable Development Criteria | - Expansion in forest cover, which is a national objective. |
| Environmental Impact Assessment (EIA) | - All afforestation projects in Romania are subject to review by the local environmental agency at the pre-feasibility study stage. - World Bank safeguard and policies are also applicable and require that an environmental management plan be drafted. |

# PCF Due-Diligence and Expected JI Process Requirements

In anticipation of JI implementation, the PCF attempts to meet the (emerging) JI requirements and modalities also with regard to a due process as far as this is possible at this time and without established JI institutions in host countries and at the UNFCCC level. The following Table contains special process level requirements the project is expected to meet.

Table 8	Other PCF and JI Requirements

| “Issue” Area | Explanation |
| --- | --- |
| Project risks | - Normal project related risks: A PCF risk assessment has been conducted to study project risks and mitigation options (a summary is available). - Kyoto Protocol related risks: Standard contractual arrangement envisaged by the PCF included an Emission Reductions Purchase Agreement with the Project Entity and a Host Country Agreement with the host country. Host Country Agreements (HCA) were intended to commit the PCF host countries to a number of obligations, the most significant being the approval of the project, including its contribution to sustainable development, transfer of emission reduction to PCF shareholders, ratification of the Protocol within a specified period of the Protocol coming into force, and being in compliance with the Protocol. The HCA is being negotiated and should be signed in the summer of 2002. Romania has ratified the Kyoto Protocol. |
| World Bank standards | The project is part of the PCF’s and World Bank Europe and Central Asia region’s project portfolios. As such is has to meet World Bank project standards, in particular safeguard policies. This is assured by the Bank task team members who follow Bank project preparation and quality assurance procedures. |
| Local stakeholder participation | As part of due diligence and the baseline study, two sets of consultations with local communities took place. These consultations have revealed that in a few areas the project might face opposition from surrounding communities. A Japanese Grant has been requested to further analyze the nature of this opposition and design, in a participatory manner, appropriate solutions taking the interests of communities into account. |
| Public comments to validator | PCF discloses the PDD, baseline study and MP on its website during the validation period and invite comments from Parties, stakeholders and NGO’s for consideration by the validator. |
| Validation | PCF has selected GFA (in partnership with TUEV) to confirm that the project meets (emerging) JI requirements (determination) and to provide a Validation Report and Opinion. GFA is a certifier under the Forest Stewardship Council, while TUEV is an ISO 14001-certified auditor. Both have notified their interest to the UNFCCC to become independent entities under JI. |

# Project Documents

The following documents have been prepared in the course of the design of the project and support the project design as presented above.

- PCF (2002): Romania Afforestation of Degraded Agricultural Land project – Project Concept Note.

- Winrock International et al. and PCF (2002):  Romania Afforestation of Degraded Agricultural Land project – Baseline Study, Monitoring Plan and Emission Reductions Projection.

- Henry Phillips and PCF (2002): Romania Afforestation of Degraded Agricultural Land project – Technical, Financial and Environmental Assessment Report.

- Malina Voicu and PCF (2002): Romania Afforestation of Degraded Agricultural Land project – Social Assessment.

- World Bank (2002) Romania Afforestation of Degraded Agricultural Land project – Project Concept Document.

- Host Country Endorsement.

# Emission Reductions Detail

The table and figure below show the annual and cumulative ERs generated by the project.

| Year | Annual tC | Cumul tC | Cumul tCO2 | Average |
| --- | --- | --- | --- | --- |
| 2002 | 1,932 | 1,932 | 7,085 |  |
| 2003 | 3,348 | 5,280 | 19,361 |  |
| 2004 | 9,337 | 14,617 | 53,597 |  |
| 2005 | 12,990 | 27,608 | 101,229 |  |
| 2006 | 15,121 | 42,728 | 156,671 |  |
| 2007 | 15,280 | 58,009 | 212,698 |  |
| 2008 | 18,156 | 76,164 | 279,270 |  |
| 2009 | 20,765 | 96,929 | 355,407 |  |
| 2010 | 23,062 | 119,991 | 439,968 |  |
| 2011 | 24,535 | 144,526 | 529,930 |  |
| 2012 | 25,313 | 169,839 | 622,744 |  |
| 2013 | 25,083 | 194,922 | 714,715 |  |
| 2014 | 19,503 | 214,425 | 786,227 |  |
| 2015 | 20,351 | 234,776 | 860,847 |  |
| 2016 | 21,286 | 256,062 | 938,896 |  |
| 2017 | 21,618 | 277,680 | 1,018,161 | 443,550 |
| 2018 | 22,899 | 300,579 | 1,102,124 |  |
| 2019 | 23,536 | 324,115 | 1,188,423 |  |
| 2020 | 23,736 | 347,852 | 1,275,457 |  |
| 2021 | 24,133 | 371,985 | 1,363,945 |  |
| 2022 | 20,748 | 392,733 | 1,440,021 |  |
| 2023 | 19,447 | 412,180 | 1,511,327 |  |
| 2024 | 20,418 | 432,598 | 1,586,193 |  |
| 2025 | 21,860 | 454,458 | 1,666,345 |  |
| 2026 | 22,077 | 476,535 | 1,747,294 |  |
| 2027 | 21,606 | 498,141 | 1,826,515 |  |
| 2028 | 20,841 | 518,981 | 1,902,932 |  |
| 2029 | 19,940 | 538,922 | 1,976,046 |  |
| 2030 | 19,026 | 557,948 | 2,045,810 | 956,181 |
| 2031 | 18,148 | 576,096 | 2,112,352 |  |
| 2032 | -36,880 | 539,216 | 1,977,125 |  |
| 2033 | -55,204 | 484,012 | 1,774,712 |  |
| 2034 | -38,559 | 445,454 | 1,633,330 |  |
| 2035 | -10,868 | 434,586 | 1,593,480 |  |
| 2036 | 1,039 | 435,625 | 1,597,290 |  |
| 2037 | 5,877 | 441,502 | 1,618,839 |  |
| 2038 | 8,300 | 449,802 | 1,649,272 |  |
| 2039 | 10,270 | 460,072 | 1,686,930 |  |
| 2040 | 12,369 | 472,441 | 1,732,283 |  |
| 2041 | 14,162 | 486,603 | 1,784,211 |  |
| 2042 | 15,025 | 501,628 | 1,839,303 |  |
| 2043 | 15,097 | 516,724 | 1,894,656 |  |
| 2044 | 14,829 | 531,554 | 1,949,031 |  |
| 2045 | 11,477 | 543,031 | 1,991,114 |  |
| 2046 | 10,861 | 553,892 | 2,030,936 |  |
| 2047 | 11,647 | 565,539 | 2,073,643 |  |
| 2048 | 13,013 | 578,552 | 2,121,358 |  |
| 2049 | 13,777 | 592,329 | 2,171,874 |  |
| 2050 | 14,239 | 606,568 | 2,224,083 | 1,330,307 |
| 2051 | 14,566 | 621,134 | 2,277,493 |  |
| 2052 | 11,215 | 632,350 | 2,318,615 |  |
| 2053 | 10,092 | 642,441 | 2,355,619 |  |
| 2054 | 11,319 | 653,760 | 2,397,122 |  |
| 2055 | 12,118 | 665,879 | 2,441,556 |  |
| 2056 | 13,241 | 679,120 | 2,490,107 |  |
| 2057 | 13,224 | 692,344 | 2,538,596 |  |
| 2058 | 12,745 | 705,089 | 2,585,327 |  |
| 2059 | 12,040 | 717,129 | 2,629,472 |  |
| 2060 | 11,321 | 728,450 | 2,670,983 |  |
| 2061 | 10,629 | 739,079 | 2,709,955 |  |
| 2062 | -44,097 | 694,982 | 2,548,266 |  |
| 2063 | -61,997 | 632,985 | 2,320,945 |  |
| 2064 | -44,834 | 588,151 | 2,156,554 |  |
| 2065 | -16,676 | 571,475 | 2,095,408 |  |
| 2066 | -4,144 | 567,331 | 2,080,212 |  |
| 2067 | 1,165 | 568,496 | 2,084,484 |  |
| 2068 | 3,919 | 572,415 | 2,098,855 |  |
| 2069 | 6,153 | 578,568 | 2,121,414 |  |
| 2070 | 8,472 | 587,040 | 2,152,480 |  |
| 2071 | 10,488 | 597,527 | 2,190,934 |  |
| 2072 | 11,525 | 609,052 | 2,233,192 |  |
| 2073 | 11,726 | 620,778 | 2,276,187 |  |
| 2074 | 11,592 | 632,370 | 2,318,691 |  |
| 2075 | 8,448 | 640,818 | 2,349,668 |  |
| 2076 | 7,888 | 648,707 | 2,378,592 |  |
| 2077 | 8,820 | 657,527 | 2,410,931 |  |
| 2078 | 10,324 | 667,850 | 2,448,784 |  |
| 2079 | 11,268 | 679,118 | 2,490,100 |  |
| 2080 | 11,902 | 691,020 | 2,533,739 |  |
| 2081 | 12,399 | 703,419 | 2,579,203 |  |
| 2082 | 9,205 | 712,624 | 2,612,955 |  |
| 2083 | 8,202 | 720,826 | 2,643,029 |  |
| 2084 | 9,542 | 730,369 | 2,678,018 |  |
| 2085 | 10,640 | 741,009 | 2,717,032 |  |
| 2086 | 11,765 | 752,774 | 2,760,171 |  |
| 2087 | 11,844 | 764,618 | 2,803,599 |  |
| 2088 | 11,474 | 776,092 | 2,845,669 |  |
| 2089 | 10,942 | 787,033 | 2,885,788 |  |
| 2090 | 10,404 | 797,437 | 2,923,937 |  |
| 2091 | 9,891 | 807,328 | 2,960,203 | PEAK |
| 2092 | -44,689 | 762,639 | 2,796,343 |  |
| 2093 | -62,513 | 700,126 | 2,567,128 |  |
| 2094 | -45,329 | 654,797 | 2,400,923 |  |
| 2095 | -16,951 | 637,846 | 2,338,768 |  |
| 2096 | -4,557 | 633,289 | 2,322,060 |  |
| 2097 | 699 | 633,988 | 2,324,623 |  |
| 2098 | 3,470 | 637,458 | 2,337,345 |  |
| 2099 | 5,706 | 643,164 | 2,358,269 |  |
| 2100 | 8,036 | 651,200 | 2,387,732 | 1,900,325 |